# Risk Register and Mitigation Plan

Generated: February 20, 2026

## Project Charter

PROJECT CHARTER

PROJECT NAME: Digital Transformation Initiative - Phase 1

PROJECT MANAGER: Robert Chen | Phone: 555-0147 | Email: r.chen@consulting.com

EXECUTIVE SPONSOR: Jane Williams, CIO

BUSINESS CASE:

Problem Statement: Legacy systems limit revenue growth by 23% YoY

Opportunity: Digital-first architecture enables $12.3M additional revenue

Strategic Alignment: Aligns with 2026 technology modernization initiative

Expected Benefits:

- Revenue increase: $12.3M over 3 years

- Cost savings: $4.1M annually

- Risk reduction: $2.1M compliance exposure eliminated

PROJECT SCOPE:

In scope:

- Legacy system assessment (89 applications audited)

- Cloud infrastructure design and implementation

- Data migration strategy and execution

- Process redesign for digital workflows

- Staff training and change management

Out of scope:

- Business process reengineering beyond digital enablement

- Third-party software implementation

- Real estate consolidation

PROJECT TIMELINE:

Start Date: March 15, 2026

End Date: September 30, 2027 (18 months)

Phase 1: Design (M1-3)

Phase 2: Pilot (M4-6)

Phase 3: Scale (M7-15)

Phase 4: Optimization (M16-18)

BUDGET: $8.2M total

- Consulting: $3.2M (39%)

- Technology: $3.1M (38%)

- Infrastructure: $1.1M (13%)

- Training/Change: $0.8M (10%)

SUCCESS CRITERIA:

- On-time delivery (within 5% schedule variance)

- On-budget execution (within 5% cost variance)

- 90%+ system uptime during migration

- User adoption rate: >85% within 60 days of go-live

- ROI realization: 60% of projected benefits by end of year 2

GOVERNANCE:

Steering Committee: Monthly (CIO, CFO, CTO, Project Sponsor)

Project Leadership: Weekly (PM, leads, key stakeholders)

Working Teams: Bi-weekly (implementation teams)

AUTHORIZATION:

Project Sponsor: _________________________ Date: _________

CFO Approval: _________________________ Date: _________

CIO Approval: _________________________ Date: _________

## Risk Register

PROJECT RISK REGISTER - Q1 2026

RISK ID: RK-001 | Executive Sponsorship Erosion

Probability: 23% | Impact: 5 (Critical)

Risk Score: 4.2/5.0

Description: CIO transition in July may deprioritize project

Mitigation: Monthly steering committee visibility, clear KPIs

Contingency: Escalation to EVP of Operations

Owner: Project Manager

Status: ACTIVE - Monitor

RISK ID: RK-002 | Talent Retention During Migration

Probability: 35% | Impact: 4 (High)

Risk Score: 3.4/5.0

Description: Key IT staff may leave during modernization

Mitigation: Retention bonuses, upskilling program, clear career paths

Contingency: Acceleration of external hiring plan

Owner: HR Business Partner

Status: ACTIVE - Monitor

RISK ID: RK-003 | Legacy System Data Integrity Issues

Probability: 28% | Impact: 4 (High)

Risk Score: 3.0/5.0

Description: 23-year-old systems may have data quality issues

Mitigation: Early data audit, remediation plan

Contingency: Extended parallel run period

Owner: Data Lead

Status: ACTIVE - Monitoring Started

RISK ID: RK-004 | Budget Overrun

Probability: 19% | Impact: 3 (Medium)

Risk Score: 2.1/5.0

Description: Scope creep or unforeseen technical complexity

Mitigation: Strict change control, fixed-price vendor contracts

Contingency: $412K contingency reserve (5% of budget)

Owner: Finance Lead

Status: ACTIVE - Monthly review

RISK ID: RK-005 | Knowledge Loss Post-Project

Probability: 31% | Impact: 3 (Medium)

Risk Score: 2.3/5.0

Description: Consulting team knowledge not transferred to internal staff

Mitigation: Documentation plan, knowledge transfer sessions

Contingency: Extended post-go-live support contract

Owner: Change Manager

Status: ACTIVE - Training plan in place

CONFIDENTIAL - INTERNAL USE ONLY